## HLE
Humelink East Project Complaints Register
Year | Month | Date | Time | Number of Complaints | How complaint was received | LGA | Topics Raised | Avoidable / Unavoidable | Summary | Responses and Investigation | Salesforce ID | Outstanding Actions | Status | Date Closed
2024 | November | 27/11/2024 | 12pm | 1 | Email | Yass Valley | Minor complaint - re: interactions with stakeholder | Avoidable | Received a complaint from the stakeholder about some interactions leading up to an event involving cultural activities. | ~ Email sent with contact details to stakeholder ~ Investigation was undertaken ~ Phone call made to stakeholder ~ Further discussions held with stakeholder ~ 13/12/2024 - Phone call and further emails with stakeholder ~ 17/12/2024 - Email sent to stakeholder ~ Complaint recorded | Activity number: ACT-88390 - ACT-89127 | Waiting on a response from the stakeholder | Open
2024 | December | 2024-12-06 | AM | 1 | Text message | Yass Valley | Participation on the project | Unavoidable | Stakeholder sent a text to complain about how they felt they weren't included in the procurement process for the project. The stakeholder advised they do not live on country anymore but felt they should still be able to be a representative working on the project. | ~ Phone call made to stakeholder on 6/12/2024 at 3pm ~ Email sent to stakeholder on 6/12/2024, advising they could participate on the project ~ Complaint recorded ~ Expression of Interest form was sent to stakeholder on 9/12/2024 | Activity number: ACT-89130 | None | Closed | 9/12/2024