## Complaints
HumeLink West Joint Venture Complaints Register
Year | Month | Date | Time received | Number of complaints | How complaint was received | Local Governent Area | Topics raised | Avoidable / unavoidable | Summary | Responses and investigation | Salesforce ID | Oustanding actions | Status | Date closed
2024 | November |  |  | No complaints registered
2024 | December | 2024-12-03 | 11:18AM | 1 | SMS | Wagga Wagga | Traffic and Transport | Unavoidable | Temporary traffic management controls (including signs and traffic lights) required for worker safety during road survey work causing delays, and obstructing heavy vehicle turning circle and line of sight when exiting and entering driveway. | Motorists cannot be delayed at temporary traffic lights for more than three minutes and most vehicles are held for less than three minutes to allow traffic through the work area. Traffic control setup was assessed as compliant to the approved traffic management plan. The temporary traffic controls were repositioned to facilitate a wider turning area for a heavy vehicle and allow for longer line of site for vehicles entering or exiting the driveway. The traffic management plan and actions taken were discussed with the stakeholder and the project team working along the road will ensure all efforts will be made to minimise delays, including traffic controllers in place to assist residents and motorists. | ACT-89702 | Nil | Closed | 2024-12-04
2024 | December | 2024-12-02 | 01:00PM | 1 | Phone call in | Wagga Wagga | Property access | Avoidable | Stakeholder reported that project team had accessed private property without notification. | Stakeholder was advised that project representative was being escorted on adjacent land and was unaware they had crossed over the property boundary into the stakeholder's property. Project teams will refer more carefully to boundary maps and not rely on escorts to ensure no unauthorised access. | ACT-89496 | Nil | Closed | 2024-12-19
2024 | December | 2024-12-09 | 08:32AM | 1 | Phone call in | Wagga Wagga | Property access | Avoidable | Stakeholder reported an internal property gate was not locked in the same position following access by the project team. | Variances in pre- and post- gate access photos were identified and alternative lock mechanisms were discussed with the stakeholder. Briefing on the specific gate lock mechanism will be provided to the project teams prior to access. | ACT-89316 | Nil | Closed | 2024-12-09
2025 | January |  |  | No complaints registered
2025 | February | 2025-02-10 | 10:59AM | 1 | Email | Wagga Wagga | Safety | Unavoidable | Stakeholder concerned with worker safety, specifically non project-related dust impacts to construction workers. | Dusty conditions are prevalent due to dry and windy weather, and non-project related vehicles passing at speed. Provided stakeholder with information on current and planned dust mitigations implemented by project team, in consultation with Wagga Wagga City Council. | ACT-93556 | Nil | Closed | 2025-02-10
2025 | February | 2025-02-10 | 8:54PM | 1 | Email | Snowy Valleys Council | Visual Impact Construction methodology Project engagement and communications | Unavoidable | Community member concerned about the visual impacts from their property, potential impacts to property value and project communication received. | Currently under investigation and response being developed. | ACT-93683 | Respond to complaint | Open
2025 | February | 2025-02-18 | 1:04PM | 1 | Phone call in | Wagga Wagga | Construction - Traffic | Unavoidable | Stakeholder concerned with large amount of traffic control resources in operation. | Temporary traffic management is implemented in accordance with approved traffic management plans and standard traffic procedures in compliance with the Transport for NSW Traffic Control at Work Sites Technical Manual. | ACT-94115 | Nil | Closed | 2025-02-18